## Activities_TA Guinea Bissau
Activities Schedule & Estimated Person-days |  |  |  |  | Estimated person-day
|  | Duration (wk.) | Start of Activity | Date Deliverable | Team Leader | National Expert | Local staff 1 | Local staff 2 | TOT
WP1 Task 1 : Conduct an assessment of the Bambadinca mini-grid |  | 1.5 |  |  | 5 | 7 | 5 | 5 | 22
1.1 | Review of existing data and documentation | 0.5 |  |  | 3 | 2 | 0 | 0 | 5
1.2 | Interviews to relevant stakeholders and beneficiaries | 0.5 |  |  | 1 | 3 | 3 | 3 | 10
1.3 | On site visit to assess the status of all equipment, performance ratio and production values | 0.5 |  |  | 1 | 2 | 2 | 2 | 7
WP1 Task 2 : Characterise unserved potential customers |  | 1 |  |  | 5 | 5 | 2 | 2 | 14
2.1 | Identify their energy needs | 0.4 |  |  | 2 | 2 | 1 | 1 | 6
2.2 | Ability to pay | 0.4 |  |  | 2 | 2 | 1 | 1 | 6
2.3 | Viability of connection to existing grid | 0.2 |  |  | 1 | 1 | 0 | 0 | 2
WP1 Other tasks |  | 6 |  |  | 11 | 19 | 10 | 11 | 51
3.1 | Propose a feasible and cost-effective solution to improve the performance of the Bambadinca mini-grid, including investment needs to correct identified deficiencies and replace faulty equipment. | 1 |  |  | 5 | 3 | 0 | 0 | 8
3.2 | Propose a feasible and cost-effective solution to connect so far unserved customers through connection to the mini-grid or if not possible through stand-alone solutions; make suggestions how to integrate the customers into the current tariff scheme of Bambadinca | 0.5 |  |  | 2 | 2 | 4 | 5 | 13
3.3 | Develop the procurement documents and technical specifications for the purchase of equipment regarding the repair/replacement works and the connection of new customers | 2.5 |  |  | 2 | 9 | 3 | 3 | 17
3.4 | Implement the required competitive procurement in line with the ECOWAS tender code, oversee the installation works of contractors and confirm the proper finalisation of the installation works | 2 |  |  | 2 | 5 | 3 | 3 | 13
WP2 Task 1 : Conduct a review of the Bissorã mini-grid |  | 1 |  |  | 4 | 5 | 3 | 3 | 15
1.1 | Interviews to relevant stakeholders and beneficiaries | 0.5 |  |  | 1 | 3 | 3 | 3 | 10
1.2 | Review of existing data and documentation | 0.5 |  |  | 3 | 2 | 0 | 0 | 5
WP2 Task 2 : Verify current status of mini-grid, incl. technical assessment of all components |  | 0.5 |  |  | 3 | 3 | 3 | 3 | 12
2.1 | On site visit(s) | 0.5 |  |  | 3 | 3 | 3 | 3 | 12
WP2 Other tasks |  | 6 |  |  | 8 | 15 | 3 | 3 | 29
3.1 | Identify problems and bottlenecks and propose a feasible and cost-effective solution, which will lead to the commissioning and operation of the plant within 2020 | 2 |  |  | 4 | 3 | 0 | 0 | 7
3.2 | Develop the procurement documents and technical specifications for the purchase of equipment related to the PV mini-grid and the distribution grid | 2 |  |  | 2 | 7 | 0 | 0 | 9
3.3 | Implement the required competitive procurement in line with the ECOWAS tender code, oversee the installation works of contractors and confirm the finalisation of the installation works | 2 |  |  | 2 | 5 | 3 | 3 | 13
Reporting |  | 6.9 |  |  | 35 | 22 | 0 | 0 | 57
| WP1 Inception report | 0.4 |  |  | 2 | 1 | 0 | 0 | 3
| WP1 Preliminary report including technical assessment of the Bambadinca mini-grid | 0.5 |  |  | 3 | 2 | 0 | 0 | 5
| WP1 Report with recommendations to improve the performance of the mini-grid | 0.4 |  |  | 2 | 1 | 0 | 0 | 3
| WP1 Report with recommendations on how to address the situation of unserved customers | 0.4 |  |  | 2 | 1 | 0 | 0 | 3
| WP1 Evaluation reports for the selection of equipment following the tenders | 0.4 |  |  | 2 | 1 | 0 | 0 | 3
| WP1 Draft Final report and confirmation of finalisation of works | 0.5 |  |  | 3 | 2 | 0 | 0 | 5
| WP1 Final report incorporating comments by ECREEE | 1 |  |  | 4 | 3 | 0 | 0 | 7
| WP2 Inception report | 0.4 |  |  | 2 | 1 | 0 | 0 | 3
| WP2 Preliminary report with an overview of the project and identified gaps and bottlenecks | 0.5 |  |  | 3 | 2 | 0 | 0 | 5
| WP2 Report with recommendations on how to proceed with the commissioning of the Bissorã mini-grid | 0.5 |  |  | 3 | 2 | 0 | 0 | 5
| WP2 Evaluation reports for the selection of equipment following the tenders | 0.4 |  |  | 2 | 1 |  |  | 3
| WP2 Draft Final report and confirmation of finalisation of works | 0.5 |  |  | 3 | 2 |  |  | 5
| WP2 Final report incorporating comments by ECREEE and other partners | 1 |  |  | 4 | 3 | 0 | 0 | 7
|  | 22.9 |  |  | 71 | 76 | 26 | 27 | 200